## Instructions
Capacity Management Workbook
Editable companion to the executive playbook and practitioner toolkit
Workflow | 1. Set assumptions. 2. Inventory and qualify demand. 3. Enter resource capacity. 4. Map skills. 5. Enter demand profile. 6. Review gaps. 7. Compare scenarios. 8. track constraints and decisions. 9. Review dashboard.
Blue text / light blue fill | User inputs and assumptions.
Black text | Formulas and derived values.
Green text | Values linked from another worksheet.
Orange fill | Review or management attention.
Light red fill | Gap, overdue item, or error flag.
Purple fill | Control or logic value.
Important | Replace example rows with organization data. Preserve formulas when adding rows.

## Assumptions
Planning Assumptions
Blue cells are editable controls used throughout the workbook
Assumption | Value | Unit | Owner | Last reviewed | Notes
Standard hours per workday | 8 | hours | EPMO | 2026-09-09 | Adjust to local policy
Default proficiency factor | 90% | factor | Functional leader | 2026-09-09 | Use role-specific value where known
Default focus factor | 85% | factor | Program manager | 2026-09-09 | Reflect context switching
Default delivery-effectiveness factor | 95% | factor | EPMO | 2026-09-09 | Calibrate from historical actuals
Default reserve percentage | 10% | percent | Portfolio governance | 2026-09-09 | Reflect unplanned work volatility
WIP escalation threshold | 10 | items | Program manager | 2026-09-09 | Illustrative control
Decision service level | 5 | business days | Governance chair | 2026-09-09 | Cross-workstream decisions

## Demand Inventory
Demand Inventory
Capture all work before prioritization and capacity allocation
Demand ID | Demand name | Sponsor | Work category | Mandatory? | Outcome / benefit | Requested start | Target date | Priority score | Status | Estimated cost | Readiness % | Primary program | Notes
D-001 | Claims intake modernization | Business sponsor | Strategic change | No | Reduce routing time and improve status visibility | 2026-10-01 | 2027-03-31 | 88 | Qualified | 450000 | 80% | Customer Operations | Example row
D-002 | Regulatory reporting update | Compliance sponsor | Regulatory | Yes | Meet required reporting obligation | 2026-09-15 | 2026-12-15 | 96 | Approved | 225000 | 90% | Compliance | Example row
D-003 | Platform maintenance | Technology owner | Technical health | No | Reduce operational risk and support load | 2026-11-01 | 2027-02-28 | 72 | Proposed | 180000 | 60% | Core Platforms | Example row

## Resource Capacity
Resource Capacity
Calculate gross, usable, effective, reserved, and committable hours by period
Resource ID | Resource / pool | Role | Primary skill | Period | Workdays | Hours / day | Gross hours | Leave | Operations | Administration | Other committed | Usable hours | Proficiency | Focus | Delivery effectiveness | Effective hours | Reserve % | Reserve hours | Committable hours
R-001 | Architecture pool | Solution Architect | Architecture | 2026-10 | 22 | 8 | 176 | 8 | 56 | 16 | 8 | 88 | 95% | 80% | 95% | 63.536 | 10% | 6.3536 | 57.1824
R-002 | Security review pool | Security Analyst | Security | 2026-10 | 22 | 8 | 176 | 8 | 72 | 16 | 0 | 80 | 90% | 85% | 95% | 58.14 | 15% | 8.721 | 49.419
R-003 | Business testing pool | Business SME | Acceptance Testing | 2026-10 | 22 | 8 | 176 | 16 | 88 | 16 | 0 | 56 | 85% | 80% | 90% | 34.272 | 10% | 3.4272 | 30.8448
R-004 | Delivery team A | Engineer | Engineering | 2026-10 | 22 | 8 | 176 | 8 | 40 | 16 | 0 | 112 | 95% | 90% | 95% | 90.972 | 10% | 9.0972 | 81.8748

## Skill Matrix
Skill and Capability Matrix
Map proficiency and deployability; 1=awareness, 5=expert
Resource ID | Resource / pool | Skill | Proficiency 1-5 | Domain knowledge 1-5 | Can work independently? | Can approve / review? | Available period | Development action | Notes
R-001 | Architecture pool | Architecture | 5 | 5 | Yes | Yes | 2026-10 | Maintain | Scarce enterprise skill
R-002 | Security review pool | Security | 4 | 4 | Yes | Yes | 2026-10 | Cross-train backup | Potential constraint
R-003 | Business testing pool | Acceptance Testing | 4 | 5 | Yes | Yes | 2026-10 | Protect test windows | Operational conflict
R-004 | Delivery team A | Engineering | 4 | 4 | Yes | No | 2026-10 | Develop reviewer skill | Delivery capacity

## Demand Profile
Time-Phased Demand Profile
Translate initiatives into role and skill hours by period
Demand ID | Demand name | Program | Skill | Role | Period | Required hours | Confidence | Dependency ready? | Priority score | Notes
D-001 | Claims intake modernization | Customer Operations | Architecture | Solution Architect | 2026-10 | 80 | 80% | Yes | 88 | Example
D-001 | Claims intake modernization | Customer Operations | Engineering | Engineer | 2026-10 | 140 | 75% | Yes | 88 | Example
D-002 | Regulatory reporting update | Compliance | Security | Security Analyst | 2026-10 | 75 | 90% | Yes | 96 | Example
D-002 | Regulatory reporting update | Compliance | Acceptance Testing | Business SME | 2026-10 | 65 | 85% | No | 96 | Business availability pending

## Gap Analysis
Demand-Capacity Gap Analysis
Positive gap indicates surplus; negative gap requires a management decision
Period | Skill | Committable capacity | Approved demand | Gap | Demand / capacity | Status | Primary constraint? | Recommended action | Decision owner
2026-10 | Architecture | 57.1824 | 80 | -22.8176 | 139.9% | SHORTFALL | No | Develop scenario and trade-off decision | Portfolio governance
2026-10 | Security | 49.419 | 75 | -25.581 | 151.8% | SHORTFALL | No | Develop scenario and trade-off decision | Portfolio governance
2026-10 | Acceptance Testing | 30.8448 | 65 | -34.1552 | 210.7% | SHORTFALL | Yes | Develop scenario and trade-off decision | Portfolio governance
2026-10 | Engineering | 81.8748 | 140 | -58.1252 | 171% | SHORTFALL | No | Develop scenario and trade-off decision | Portfolio governance

## Scenarios
Scenario Comparison
Compare explicit options when demand exceeds committable capacity
Scenario ID | Scenario name | Description | Scope impact | Date impact | Incremental cost | Capacity action | Capacity change | Constraint effect | Risk level | Outcome impact | Reversible? | Recommendation | Decision owner | Decision date
S-001 | Current plan | Maintain all current commitments | None | Likely delay | 0 | None | 0 | No improvement | High | Outcome timing at risk | Yes | No | Portfolio governance
S-002 | Defer lower priority | Pause D-003 and reassign capacity | Reduce lower-priority scope | Protect D-002 date | 0 | Reallocate | 40 | Improve | Medium | Protect mandatory outcome | Yes | Recommended | Portfolio governance
S-003 | External support | Add temporary specialist capacity | None | Protect target | 75000 | Source | 80 | Improve after ramp-up | Medium | Protect both outcomes | Partly | Alternative | Executive sponsor

## Constraint Register
Constraint Register
Track evidence, exploitation, subordination, elevation, and movement
Constraint ID | Constraint | Type | Evidence | Affected outcome | Queue size | Oldest age (days) | Lost hours / period | Exploit actions | Subordinate actions | Elevate actions | Owner | Review date | Status
C-001 | Security review capacity | Skill / approval | Demand-capacity ratio above 1.0; queue growing | Regulatory reporting | 6 | 12 | 18 | Improve intake quality; protect reviewer time | Limit upstream release; prioritize mandatory work | Source backup reviewer | Security leader | 2026-09-16 | Active

## Decision Log
Capacity Decision Log
Make trade-offs explicit, dated, and accountable
Decision ID | Decision required | Recommended action | Decision owner | Date raised | Due date | Status | Decision | Decision date | Displaced work | Outcome impact | Consequence of delay | Notes
DEC-001 | Resolve October security capacity shortfall | Defer lower-priority review and protect mandatory work | Portfolio governance | 2026-09-09 | 2026-09-14 | Open |  |  | Platform maintenance | Protect compliance date | Queue grows and milestone confidence falls | Example

## Dashboard
Capacity Management Dashboard
Executive view of demand, committable capacity, gaps, constraints, and decisions
KPI | Value | Interpretation
Total committable capacity | 219.321 | Hours available after effectiveness and reserve
Total profiled demand | 360 | Time-phased required hours
Net capacity gap | -140.679 | Negative indicates overload
Demand / capacity | 164.1% | Above 100% indicates overload
Active constraints | 1 | Current documented constraints
Open decisions | 1 | Capacity decisions awaiting action
Overdue decisions | 0 | Open decisions past due
Skill | Capacity | Demand | Gap
Architecture | 57.1824 | 80 | -22.8176
Security | 49.419 | 75 | -25.581
Acceptance Testing | 30.8448 | 65 | -34.1552
Engineering | 81.8748 | 140 | -58.1252
Leave | 10
Operations | 20
Reserve | 15
Committable | 55
Active Constraints | 3
Open Decisions | 5
Overdue Decisions | 1